## Sheet1
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 11
19 |  | a1835151
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-23 | 10:00 | 17:00 | 7 | Work on testing plan | Test is every important for the project, it will check the implement and make the code more efficiency. | Complete the testing plan draft.
Tuesday | 2022-05-24 | 12:00 | 20:00 | 8 | 1.Team meeting, discuss the progress of all the team member. 2.Continue to improve the testing plan. | Complete the testing plan before deadline. | Complete the testing plan.
Wednesday | 2022-05-25 | 14:00 | 16:00 | 2 | Make a replacement list for all the team members to reduce the project risk. | In order to aviod the influence of covid-19 and other risks, every two people needs to be played a replacement roles,in case some one cannot work for some reasons. | Complete as wished.
Thursday | 2022-05-26 | 10:00 | 20:00 | 10 | Code overview and fix the completed part, make the code clean. | This step is helpful to the whole team, make the code more readable and in the same logic. | Complete the task.
Friday | 2022-05-27 | 17:00 | 19:00 | 2 | Team meeting, get to know what the whole team had done. | Help knowing the progress of the whole group and adjust the codeing plan from time to time. | Prepare to be a substitute, work with other team members.
Saturday | 2022-05-28 | 12:00 | 17:00 | 5 | Learn how to extract the join statement. | Help the other team member to complete his task. | Continue learning.
|  |  | Total | 34