## Sheet1
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 4
19 |  | a1835151
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-21 | 12:00 | 18:00 | 6 | Prepare for the pitch presentation, attending the lecture, team meeting making conclusion of what we currently got for the understanding of everthing the projet | Seems that we have already know everything but doing little about it. | Combine all the team members' research result and make a clear show in the slides.
Tuesday | 2022-03-22 | 11:00 | 18:00 | 7 | Make draft slides for myself and learn relavant knowledge about that. | Learning the data mapping and data dictionary. | Catching up the client's requirements.
Wednesday | 2022-03-23 | 11:00 | 21:00 | 10 | Complete draft of the pitch slides, team meeting giving comments of the drate pitch slides with each other, collecting questions about the client meeting. | Finish the Pitch Slides for the project. Make sure the client meeting had a good feedback. | Writing the draft of the presentation.
Thursday | 2022-03-24 | 18:30 | 20:30 | 2 | Workshop and client meeting with the client to talk about how to improve the pitch slides and the progress of the project. | Improve the team pitch slides for the project | The client gave very useful feedbacks of our slides and provided suggestions to improve the strcture of the slides so that our pitch slides will have another new version
Friday | 2022-03-25 | 10:00 | 15:00 | 5 | Team meeting discussing about the ideas suggested by the client and make a plan to enhance our project pitch slides | We planned to start working on the pitch presentation starting from today. However, since we need to have a big change of the pitch slides, we spent most of our meeting time working on the pitch slides | Edit the pitch slides multiple times and complete the final version.
Saturday | 2022-03-26 | 12:00 | 15:00 | 3 | Confirming the final allocation of the presentation for every team member, everyone start working on the pitch presentation by following the latest version of the slides | Catch up what we supposted to start yesterday about the pitch presentation | Practise for the Pitch presentation and make sure to finish my part in 2.5minutes.
|  |  | Total | 33