## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 5
19 |  | a1788871
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-28 | 15:00 | 21:00 | 6 | Complete the pitch presentation by following the pitch slides, attend the weekly lecture, try to understand what the project requirements provided by the client | For the pitch presentation, it still fit to our project plan, however the requirments need to be fully understood as soon as possible | Copmlete the first draft of the pitch presentation individually, learn new knowledge from the lecture and partially understood the requirements of the project that the team need
Tuesday | 2022-03-29 | 18:00 | 20:00 | 2 | General group meeting to give comments for the individual pitch presentation parts with each other | Everything seems going well because we tried to make further improvement for the pitch presentation | Every team member's pitch presentation seems well completed but still need to improve, try to combine the final version of pitch presentation by tomorrow noon
Wednesday | 2022-03-30 | 12:00 | 21:00 | 9 | Complete the final version of the individual pitch presentation, second group meeting, combine the individual pitch presentation together | Get stuck at some points while combing the pitch presentation videos due to unknown reasons, submit the pitch presentation youtube link very close to the due time of the assignment which is unexpected, but at least we did it finally | Complete the pitch presentation for the whole group
Thursday | 2022-03-31 | 17:00 | 19:00 | 2 | Doing more research on the project requirements provided by the client | Get more ideas to fit the requirements of the project | Mostly understood the functions that the project is supposted to achieve
Friday | 2022-04-01 | 17:00 | 10:00 | 5 | Third group meeting discussing about the role allocation of the business case & draft plan | Make the allocation of the business case & draft plan to get ready for the assignment | Every team member get ready for what the team need to do for the businees case & draft plan
Saturday | 2022-04-02 | 18:00 | 0:00 | 6 | Start doing research for the parts that I contribute for the business case & draft plan | Catch up the project plan while learning dundamental knowledge of the project to write the business case & draft plan | Get a number of ideas that could be useful for the business case & draft plan
|  |  | Total | 30