## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 7
19 |  | a1788871
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-25 | 20:00 | 23:00 | 3 | Catch up all the new knowledge and get ready for the second half of the semeter. | In my personal schdule, it is a transition period from mid-term break to the second half of the semester because it will be getting much more work to do. | Revised what what had completed before the mid-term break and catch up the speed of study.
Tuesday | 2022-04-26 | 14:00 | 20:00 | 6 | First genral group meeting to catch up with each other in the team. Watch the lecture recordings. | Allocate new tasks of the team to keep processing the project. Clarify every step of the project. | Update every team member's progess, get ready for processing the project with the team. Catchup what the lecturer taught by watching the lecture recording.
Wednesday | 2022-04-27 | 15:00 | 21:00 | 6 | Comlete the data extraction and doing research of how to process the input files and accept by the system. | Start trying to input files and generate output in the created webpage. | Successfully extracting data catalog. Successfully generate the ouput page.
Thursday | 2022-04-28 | 17:00 | 22:00 | 5 | Start anaylsing how to write the milestone1 report. General client meeting to discusss the features of our software and present the update of the project. | After the half of the semester, the project should show something out to the client and get feedback to make further enhancement. | Had a brief understanding the structure of the milestone1 report and know how to write the milestone 1. Received feedback from the client about our work.
Friday | 2022-04-29 | 15:00 | 21:00 | 6 | Second genral group meeting to discuss what the client said and what the team should do in the following days. Allocate the role to write the milestone1 report. | Get ready for starting new tasks of the project, by getting feedback from the client and allocating the structure of the milestone1 of the project. | Know what the team should improve and what are the tasks that in high priority we need to do. Start writing the milestone1 report.
Saturday | 2022-04-30 | 15:00 | 21:00 | 6 | Start working on milestone1 report. Learn how to create a small window to store details of the input data showing in the webpage by using javascript. | Processing the milestone1 of the project. Get new challenge of the front-end deployment. | Contribute on the reflection parts of the milestone1 report and write something new in the report.
|  |  | Total | 32