## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 10
19 |  | a1809187
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-16 | 10:00 | 17:00 | 7 | Start working on the testing plan, and improve the showing detailed information function to show the number of edges that links to the node. | Testing is important for a software project and showing the extra information for the node is required by the client. | Finished some part of the testing plan and assigned tasks to each team member.
Tuesday | 2022-05-17 | 10:00 | 15:00 | 5 | Complete the function of showing the number of edges that links to the node. Start working on the search function to show the searched node and nodes that links to it. | The search function is one of the most important function for the data flow map since there is no way users could find useful information in a graph that has many nodes without searching function. | the function of showing the number of edges that links to the node is completed.
Wednesday | 2022-05-18 | 12:00 | 17:00 | 5 | Complete the search function to show the searched node and nodes that links to it. | The search function is one of the most important function for the data flow map since there is no way users could find useful information in a graph that has many nodes without searching function. | Search function completed.
Thursday | 2022-05-19 | 14:00 | 17:00 | 3 | Attend the meeting after the workshop to discuss the progress of the project.Help to record the video for testing the data flow map search function as required by the client. | It is important to report the progress regularly and also test the function is working or not. | same as task.
Friday | 2022-05-20 | 17:00 | 22:00 | 5 | Complete the function of sizing nodes according to the number of edges link to the node. Make the list of tasks left. | After disscussing with the client, we realised that there are still a lot of tasks left to do. So it is important to assign tasks to each members | List and sizing function completed.
Saturday | 2022-05-21 | 12:00 | 17:00 | 5 | Improve the search function based on the feedback given by the client. | The search function is one of the most important function for the data flow map since there is no way users could find useful information in a graph that has many nodes without searching function. | Continue improving.
|  |  | Total | 30