## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 11
19 |  | a1809187
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-23 | 10:00 | 17:00 | 7 | Complete the function of setting different colors for nodes according to their type or other attributes. Record the video for testing static graph, search function and color function. | Testing is helpful to find bugs, and color function is one of the requirements. | Complete the color function recorded the video for testing.
Tuesday | 2022-05-24 | 16:00 | 19:00 | 3 | First group meeting discussing the progress of the team.Complete the testing plan. Try to improve the search function because there is some bugs found about this function after the testing. | Testing plan is due today and we have a lot to improve. And bug fixing is a big part in software engineering. | Testing plan completed. Perfected the search function for showing the first level connections.
Wednesday | 2022-05-25 | 11:00 | 18:00 | 7 | Try to acheve the all-level relationship between nodes when searching the node. And try to show the relationship in another way in order to improve the efficiency. | The search function is one of the most important function for the data flow map since there is no way users could find useful information in a graph that has many nodes without searching function.And since I have achieved the first-level, I want to try to achieve all-level relationship. | It is difficult to acheve the all-level relationship between nodes when searching the node in the original way. But I found another way to show it.
Thursday | 2022-05-26 | 14:00 | 17:00 | 3 | Achieve the exact matching instead of fuzzy matching since the fuzzy matching can be confused sometimes.Start working on the upload file function. | After disscussing with the client, I realised that it is better to Achieve the exact matching instead of fuzzy matching since the fuzzy matching can be confused sometimes. | Exact match completed. Try to find some ways to achieve the upload function.
Friday | 2022-05-27 | 17:00 | 19:00 | 2 | Second gereral group meeting discuss the current progress of every team member's work.Continue to work on the upload file function. | It is important for users to have a place to upload their own dataset because it is impossible for users to copy their file into the code folder when they want to see their own data. | Upload file function for data flow map page completed.
Saturday | 2022-05-28 | 12:00 | 15:00 | 3 | Record video for showing the features that we have completed so far. Help to complete the meeting minutes.Check if other team members need my help. | It is important to receive feedback from the client especially its near the end of the project. | Video recorded.
|  |  | Total | 25