## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 12
19 |  | a1809187
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-30 | 12:00 | 20:00 | 8 | First group meeting disucssing every team member's work in the last week and see if anywhere needs help. Help to complete the meeting minutes. Attend lectures. | Check everyone's progress to avoid any potential delay. | project progress smoothly.
Tuesday | 2022-05-31 | 14:00 | 19:00 | 5 | Attend client meeting to show our project.Work on the upload function for subquery and case statement page. | Show the current features to the client to receive feedback. The upload function is necessary for the two pages. | attended the meeting and be the one to present.
Wednesday | 2022-06-01 | 11:00 | 19:00 | 8 | Complete the upload function for subquery and case statement page. Improve the current code structure to fix bugs. | The upload function is necessary for the two pages.The project has some bugs caused by messy code structure which need to be fixed. | upload function for the two pages completed. Bugs solved.
Thursday | 2022-06-02 | 14:00 | 18:00 | 4 | Change the layout of the subquery and case statement page according to client's feedback.Try to improve the search function to increase efficiency. | The client requires specific layout for the two pages, and the search function need to be improved. | layout of the subquery and case statement page completed.
Friday | 2022-06-03 | 17:00 | 19:00 | 2 | Try to improve the search function to increase efficiency.Create a new page and upload button for data catalog page. | the search function need to be improved. The client requires a new page for showing uploaded data catalog. | new page and upload button for data catalog page completed.
Saturday | 2022-06-04 | 12:00 | 17:00 | 5 | Improve the page layout. Create the filter function for data catalog page. | Since its near the end of the project, we need to improve the page layout to improve user experience; And the filter function would be useful for users to find objects. | Layout improved and filter function completed.
|  |  | Total | 32