## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 7
19 |  | a1809187
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-25 | 18:00 | 22:00 | 4 | Work on the milestone report. Try to figure out a better way to store the data in order to improve the efficiency to generate the graph. | The milestone report could help us figure out our project progress. And improve the efficiency to generate the graph could help to increase the user experience. | Milestone report started, and set the target to deliever a draft before the meeting on Thursday
Tuesday | 2022-04-26 | 10:00 | 17:00 | 7 | Work on the parse case function, assign each part of the milestone report to team members. Transfer the uploaded csv file into the required data structure for the project | The parse case statement function became more important from this week, so I decideded to put this task as high priority. Also, assign tasks to each team member is also an important method to increase efficiency. | Continue working.
Wednesday | 2022-04-27 | 12:00 | 19:00 | 7 | Continue working on the case function, milestone report and data structure transfer. Communicate with client through slack to get some feedback. | We need to report our current progress to the client to get some feedback. | Continue working, reported our progress to the client.
Thursday | 2022-04-28 | 13:00 | 15:00 | 2 | Complete my part of milestone report and continue working on the case function and data structure transfer. Also complete the agenda. | Complete the milestone report as soon as possible to spend more time the code. | Complete the Team reflection on progress part for milestone report and agenda.
Friday | 2022-04-29 | 17:00 | 21:00 | 4 | Complete the data structure transfer for frontend data flow map in order to show the graph after uploading the file. | Uploading is a big function for the project since the user need to upload their own dataset to see the reslut. | Function complete. Now the user could upload their own dataset.
Saturday | 2022-04-30 | 12:00 | 15:00 | 3 | Improve the milestone report | Complete the milestone report as soon as possible to spend more time the code. | Continue working.
|  |  | Total | 27