## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 10
19 |  | a1811379
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-16 | 10:00 | 18:00 | 6 | Group meetings to show the progress of each person's code work, collect those problems that cannot be solved in the group, and help each other. | Make sure nothing is missing. | Solves many problems that individuals could not solve alone.
Tuesday | 2022-05-17 | 10:00 | 15:00 | 5 | Learn how Pandas works and figure out why the data flow map page is slow to render. | In order to adjust some configurations of the dataflow map page, it is necessary to understand how Pandas works. | Figured out how Pandas works.
Wednesday | 2022-05-18 | 12:00 | 17:00 | 5 | Make the data flow map static and improve the speed of data flow map page display. Add size and color properties to node. | Improve the operational efficiency of the project. | Added size and color properties to node. Successfully made data flow map static.
Thursday | 2022-05-19 | 14:00 | 17:00 | 3 | Discuss with teammates the division of labor for the seminar presentation tomorrow. | Make us show the project more clearly. | Record the video of the workshop and upload it to the google drive.
Friday | 2022-05-20 | 17:00 | 19:00 | 2 | Participate in a workshop to demonstrate the search function of the data flow graph to the client. | Let the client know the progress of our project. | The search function is shown to the client.
Saturday | 2022-05-21 | 12:00 | 18:00 | 6 | New task: complete case statement and subquery visualization. | Based on customer feedback, we also need to visualize case statements and subqueries, which is an important part of the front-end. | Found some of the knowledge needed.
|  |  | Total | 27