## Sheet1
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 2
19 |  | a1835151
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-07 | 12:00 | 18:00 | 6 | Attend the lecture in zoom, discuss the topic of our project with the team members. | Getting much more information about the team members and the project topic. | Successfully form a great team and understand the timeline of the project.
Tuesday | 2022-03-08 | 14:00 | 17:00 | 3 | Attend the workshop for week2, had a client meeting, after that had a team meeting. | Getting much more information about the client requirement. | Knowing what the knowledge of the project and the knowledge I should learn. Plan to start doing research soon.
Wednesday | 2022-03-09 | 14:00 | 20:00 | 6 | Recording all the questions and the answers during the client meeting, post all the hand writing information to the team chat in Wechat. And wrote Minutes. | Compared the two topic about the same project and discussed which one to be choose. | All the knowledge is new.Complete the meeting minutes.
Thursday | 2022-03-10 | 14:00 | 17:00 | 3 | Discussed the new project topic by zoom meeting. | Searching information about the second topic. | Much more formilar about the second topic.
Friday | 2022-03-11 | 17:00 | 21:00 | 5 | Attend the workshop about making presentation. Started to learn how to use the open source tool about the second topic. | Knowing how to make a prefect presentation. | Confirm the project topic with the client.
Saturday | 2022-03-12 | 15:00 | 21:00 | 6 | Watch the recording for the first client meeting, start learning python and SQL | Make sure the responsibility of every team member | Learning how to use the open source tool.
|  |  | Total | 29