## Sheet1
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 5
19 |  | a1835151
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-28 | 10:00 | 16:00 | 6 | Complete the pitch presentation, attend the weekly lecture, read the requirements provided by the client | The pitch presentation could help us understand the project better, and the requirement provided by clients is helpful for us to make next move | Copmlete the first draft of the pitch presentation individually, try to turn the client requirement in to reality.
Tuesday | 2022-03-29 | 14:00 | 18:00 | 4 | Group meeting to discuss the individual pitch presentation parts with each other, made some changes. | The modification improve the pitch presentation a lot, and help the team make a better understanding for the whole project. | Combine all the team member's pitch presentation together in a confortable and smoothly way.
Wednesday | 2022-03-30 | 10:00 | 23:00 | 13 | Complete the final version of the individual pitch presentation, attend group meeting, combine the individual pitch presentation together | Get stuck while combing the pitch presentation videos due to unknown reasons, submit the final version in the end with the whole teams' effort. | Combine and submit the pitch presentation on time.
Thursday | 2022-03-31 | 16:00 | 17:00 | 1 | Attend workshop and answer some questions. | Learn from other groups and ask some questions about our own project. | Make a futher step on getting input data.
Friday | 2022-04-01 | 17:00 | 22:00 | 5 | Group meeting, discussed role allocation of the business case & draft plan | Make the allocation of the business case & draft plan to get ready for the assignment. | Everyone knows what and how to deal with the draft.
Saturday | 2022-04-02 | 12:00 | 15:00 | 3 | Confirming the final allocation of the Business Case & Draft Plan and work on it. | Complete the Business Case & Draft Plan as soon as possible. | Improve the Business Case & Draft.
|  |  | Total | 32