## Sheet1
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 8
19 |  | a1835151
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-02 | 10:00 | 19:00 | 9 | 1.Team meeting discuss what to show in the coming client meeting. 2.Try to parse case statement. | 1.Shows what the team have done and what to be done under the client's requirement. 2.Parse the statement is the first step for the second part of our project. | 1.The data flow map is not as good as we wish, needs to optimize since the loading time is too long. 2.Parse the case statement.
Tuesday | 2022-05-03 | 12:00 | 18:00 | 6 | 1.Attend the workshop on campus. 2.Milestone report improvement. | Knows one of our team member has alreay make a progress on parsing the case statement. | The whole team is behind other groups, we need speed up.
Wednesday | 2022-05-04 | 14:00 | 17:00 | 3 | Team meeting to discuss the feedback from the client about the code part. | Better known on coding part. | Speed up and fix the code.
Thursday | 2022-05-05 | 16:00 | 18:00 | 2 | Attend the workshop online | Get some clinet feedback about the milestone report. | Improve the milestone report.
Friday | 2022-05-06 | 14:00 | 17:00 | 3 | Team meeting to discuss making a task list. | Followed the client's requirement, and it help the team to division of labor and cooperation. | Make the task list.
Saturday | 2022-05-07 | 9:00 | 17:00 | 8 | 1. Design the minutes writing template. 2. Modify the minutes. | Help to improve the project management. | Continue to modify the minutes.
|  |  | Total | 31