## Sheet2
MCI Project Weekly Time Sheet
Team |  | Student ID |  |  |  | Week starting: | 8
19 |  | a1809187
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-02 | 18:00 | 23:59 | 6 | Complete the parse case statemtn function. | Parse case statement function is a big part of our project. Need to complete it as soon as possible and test it. | Function complete. Now the project could parse SQL query into case statement.
Tuesday | 2022-05-03 | 13:00 | 18:00 | 5 | Attend the workshop at the end in the afternoon to demonstrate and test the code to the client. Also work on the milestone report improvement. | It is important to show new features and code to the client to get some feedback and then improve. | Complete demonstration, Asked a few questions about the project.
Wednesday | 2022-05-04 | 12:00 | 19:00 | 7 | Work on the parse join statement function and milestone report. Send code to the client for testing. | Since the parsing subquery and case statement functions have been completed, the next task is to complete the join statement parsing function. | Continue working.
Thursday | 2022-05-05 | 14:00 | 17:00 | 3 | Attend the lecture and workshop to receive some feedback about the milestone report from tutors.Summarize what we have done so far and what we have left. | It is important to know the project progress and we have left for the rest of the project. | Improved the milestone according to the feedback.
Friday | 2022-05-06 | 17:00 | 21:00 | 4 | Make the list of the activities that we are working on, due dates and team member in charge of the activities. Also work on improving the case statement extraction. | The client required us to make a list of activities, and I think it is useful for us the know the progress and assign tasks. | List completed.
Saturday | 2022-05-07 | 12:00 | 16:00 | 4 | Check several open source projects given by the teacher, and try to find the one that is suitable for our project. | Since it is almost impossible for us to complete such as complex project from the scratch in one semester, we need to based on some similar project and improve it based on our requirement. | Decided to based on the Jaal project.
|  |  | Total | 29